## Sheet1
ID | Task | Priority | Time Estimation |  | Priority scale: 1 = most important, 2 = relatively important, 3 = least important
1 | Create working frogger game | 1 | 10 | Sprint 1 | Time estimation is scaled in days
2 | Create Menu for starting the game | 2 | 3
3 | Add better sprites to the game | 3 | 2
4 | Add sounds to the game | 2 | 2 | Sprint 2
5 | Implement Space Invaders Minigame | 1 | 10
6 | Implement Maze Minigame | 1 | 10
7 | Implement Other Minigame | 3 | 10 | Note: this was not implemented in final game
8 | Implement Scoreboard | 2 | 3
9 | Implement Scrolling display | 2 | 3